## Sink_Sheet
Property Overview |  | Existing SAP Data |  | Measure Included? |  | Proposed Fabric First Measures Specification |  |  | Installation Sequence
Property Address | 3, St. Blaises Road, CHICHESTER, PO18 0EJ | EPC Rating | D66 | Yes | Ventilation: | Trickle Vents | No
Property Reference | TBC | Floor Area (Box 4) | 59 sqm |  |  | dMEV | Yes | Upgrade wet room ventilation to dMEV units - Greenwood CV2GIP Unity or equivalent | 1
Local authority | Chichester District Council | Heat transfer coeff.(Box 39) | 174 |  |  | Door undercuts | No | Location Specified on DS-CM-11
EPC Score ( Rd SAP) | D67 | Space Heating (Box 99) | 220 | Yes | Loft Insulation: | Knauf Insulation Loft Roll44, 400 mm total thickness to provide u-value of 0.11 W/m2K |  |  | 2
Tenure | Social Housing |  |  | No | Cavity Wall Insulation:
Remedials -damp & mould present? | Yes | Proposed SAP Data |  | No | External Wall Insulation
Retrofit assessment has been carried out? | Yes | EPC Rating | C77 | No | Internal Wall Insulation:
Planning Application Ref | No | Floor Area (Box 4) | 59 sqm | No | Under Floor Insulation:
Planning Notes | No | Heat transfer coeff.(Box 39) | 159 | No | Flat Roof Insulation: |  |  |  |  | PV | Solar water Heating | Floor Insulation | Low energy lights | Room-in-roof insulation | Flat roof insulation | Hot water cylinder | Insulated doors | Draught-proofing | Upgrade boiler, same fuel | Heat recovery system for mixer showers
Building Regulation Application Ref | No | Space Heating (Box 99) | 75 | No | Room-In-Roof Insulation:
Building Regulation Notes | No | NetZero EPC Rating | TBC by Retrofit coordinator | No | Windows:
Age of Property | 1967-1975 |  |  | No | Doors:
Construction Type | Cavity Wall |  |  | No | Other please specify:
Typology | Mid -Terrace House
Stories | 2 |  |  | Measure Included? |  | Proposed Renewables Specification |  |  | Installation Sequence
Number of Bedrooms | 2 |  |  | No | Boiler/FTCH:
Site Exposure Level | Moderate |  |  | No | ESH:
Traditional Building | No |  |  | No | ASHP:
Conservation Area | No |  |  | No | GSHP:
Listed Building | No |  |  | No | Solar Thermal:
TPOs | No |  |  | Yes | Solar PV: | System Design by MCS Installer. 2.4 kWp system min. as per client spec. | Solar PV: Property Orientation | West | 3
Access Constraints | No | [5 empty] | Solar PV: Over - Shading | None or little
Vulnerable tenant present? | No
NB Where multiple measures are installed, the building services are to be commissioned at the end of the installation at the same time
Measures defined as "Net Zero Measures' MTIP